## Fill in
Management of Change (MOC) Template
qhsetech.com/templates/management-of-change-template ¦ General template, not legal or certification advice. Adapt it to your own procedures and to the requirements that apply to you. ¦ Free template by QHSEtech, CC BY 4.0: reuse and adapt it with credit (see the About sheet)
Field | Entry | Why it matters
MOC reference # |  | Ties the change to its pre-startup review, permits, any bypass record and marked-up drawings.
Change type |  | A temporary change needs an end date and a check that the plant went back; US nonmandatory guidance says temporary changes are subject to management of change.
What is changing |  | Paragraph (l)(1) covers process chemicals, technology, equipment, procedures and facilities, and HSE notes that organisational change is often analysed less thoroughly than plant change. The boxes make someone name the kind.
Is this a replacement in kind? |  | Paragraph (l)(1) exempts replacements in kind, which the US standard defines as one that satisfies the design specification. Naming who confirmed it, and against what, turns the exemption into a recorded decision.
Scope (what / why) |  | Lets an approver see exactly what they are approving and why it is needed.
Technical basis for the change |  | Carries the technical basis, (l)(2)(i).
Risk evaluation |  | Carries the impact on safety and health, (l)(2)(ii). The third column covers the time the plant runs half-changed.
Planned end of the temporary change |  | US guidance asks for a time limit for temporary changes to be established and monitored, and (l)(2)(iv) asks for the necessary time period. The maximum is your own procedure's; the form supplies none.
Stakeholder review and approval |  | Carries the authorization requirements, (l)(2)(v); five functions must each say yes or no.
Independent of the requester? |  | The US text asks for authorization requirements but does not say who must authorise, and HSE says independent reviews of plans and assessments help against loss of objectivity. The rule printed under the table is this form's own.
Pre-startup review |  | Where paragraph (i) applies, a pre-startup safety review is required for a modified facility when the change is significant enough to alter the process safety information. The first four checks follow its list; the others are the form's own.
Training and communication |  | Meets (l)(3): affected operating, maintenance and contract employees before start-up.
Implementation plan |  | Gives the document updates of (l)(2)(iii), (l)(4) and (l)(5) an owner and a date, next to the work itself.
Verification at 30, 90 and 180 days |  | This form's own follow-up convention for checking the change works as intended; HSE notes that effects of change can be subtle or delayed.
Return to original check |  | US nonmandatory guidance says management of change is used to return equipment and procedures to their original or designed conditions at the end of a temporary change.
Closure checks |  | Stops the record closing while an action, a document update, a training line or a temporary change is still open.
Lessons learned |  | Records what the next similar change should do differently; HSE says lessons from a change should be used to amend the organisation's own change procedure.

## Example (illustrative)
Illustrative example: invented, describes no real organisation
Temporary flexible hose in place of a corroded pipe section (invented plant)
Section | Entry
Change description | MOC-2026-052 · Temporary · raised 8 June by the area engineer · Replace a corroded 3 m section of DN50 solvent transfer pipe with a flexible hose assembly for up to 21 days while a new section is made. Technical basis: the new section has an 18-day lead time; the hose assembly is rated above the line's design pressure and temperature, is compatible with the solvent and has a test certificate. Not a replacement in kind: a different type of component. Related permit: PTW-1187 for cutting out the old section (the permit controls that job; this record approves the temporary hose). No bypass record.
Temporary change: time limit and return to original | Start 10 June · planned end 1 July (21 days) · maximum under the site's own procedure 28 days. Return to: DN50 carbon steel section per drawing P&ID-114 revision C, pressure tested before it goes back in service. Restoration checked by the maintenance supervisor.
Risk evaluation | Pre-change 2 × 4 = 8. With the hose and no extra controls 4 × 4 = 16. With restraints at both ends, a daily inspection and an exclusion zone while pumping, 3 × 4 = 12, accepted for 21 days only. Transition (old section out under the permit) 2 × 4 = 8.
Approval | Operations, EHS, engineering and maintenance approve on the form on 9 June · Operations manager approves 9 June · The area engineer who raised the change does not sign; the engineering approver is a piping engineer from another team and is recorded as the independent approver · Condition: daily inspection signed on the round sheet
Pre-startup review, training and communication | 10 June before the first transfer: hose certificate and both restraints checked by the maintenance supervisor, not the requester; operating procedure OP-12 marked up; all four shift crews and the contract tank-cleaning crew told about the daily check and the exclusion zone.
Implementation plan | Mark the hose on the P&ID-114 working copy (engineering, 10 June) · Add the daily inspection to the round sheet (operations, 10 June) · Fit the hose and restraints (maintenance, 10 June) · Remove the hose, fit the new section and pressure test it (maintenance, by 1 July)
Return to original and closure | 1 July: hose removed, new section fitted, pressure test passed, checked by a second maintenance technician; P&ID mark-up and round-sheet entry removed; crews told. 30, 90 and 180 day checks marked N/A: temporary change reversed on 1 July. Lesson: keep a spare section for this line. Closed 2 July by EHS, checked by someone other than the requester.

## About
Template | Management of Change (MOC) Template
Printable form | /downloads/templates/management-of-change-template.pdf
Page | https://qhsetech.com/templates/management-of-change-template
Last updated | 2026-10-20
Note | General template, not legal or certification advice. Adapt it to your own procedures and to the requirements that apply to you.
What this workbook is | A spreadsheet for typing and for keeping a log. The PDF is the printable form. This file adds no formula and no rule.
Licence and source | Creative Commons Attribution 4.0 International (CC BY 4.0), https://creativecommons.org/licenses/by/4.0/. You may copy, adapt and share this file, also commercially, if you give credit, link to the licence and say if you changed it. Credit line: Management of Change (MOC) Template by QHSEtech (https://qhsetech.com/templates/management-of-change-template), licensed under CC BY 4.0 (https://creativecommons.org/licenses/by/4.0/). Template page: https://qhsetech.com/templates/management-of-change-template