## Fill in
Pre-Startup Safety Review (PSSR) Template
qhsetech.com/templates/pre-startup-safety-review-template ¦ General template, not legal or certification advice. Adapt it to your own procedures and to the requirements that apply to you.
Field | Entry | Why it matters
Facility or unit |  | One review covers one facility or unit and one change, so the checks, the open items and the decision can be tied to a single piece of plant.
Change or project reference |  | Links the review to the management of change record that approved the change; the US rule asks that a modified facility meet the management of change requirements before start-up. A turnaround or project number is a second link.
Scope of the change |  | The US rule requires a review for new facilities and for modified ones when the modification is significant enough to change the process safety information; a replacement in kind that satisfies the design specification is outside management of change. The box makes someone state which applies.
Reviewers |  | Shows who looked at what and whether they were independent of the design and construction, so a signature can be read as 'I checked groups C and E'.
Construction and equipment per design |  | First matter in paragraph (i)(2): construction and equipment are in accordance with design specifications. Eight rows keep the walk-down, testing, relief devices and instruments each answerable.
Safety systems |  | Detection, shutdown, safety instrumented functions, fire protection and emergency equipment are the protection that must work when the first chemicals are introduced. These rows come from the earlier checklist.
Safety, operating, maintenance and emergency procedures in place |  | Second matter in paragraph (i)(2): the procedures are in place and adequate. HSE adds that commissioning needs full written instructions and that start-up is the practical test of the earlier preparations.
Process hazard analysis and recommendations |  | Third matter in paragraph (i)(2): for a new facility a process hazard analysis has been performed and its recommendations resolved or implemented before startup; the US rule also requires the resolution to be documented.
Training and personnel |  | Fourth matter in paragraph (i)(2): operator training is complete. The form adds maintenance staff, contract employees, the briefing and shift handover, because a start-up often crosses a shift change.
Management of change requirements met |  | Modified facilities must meet the management of change requirements before start-up: the change approved first, affected people informed and trained, and the actions closed or accepted with a recorded basis.
P&ID and documents updated |  | The US rule requires the process safety information and operating procedures to be updated when a change alters them. Drawings that do not match the plant are the root of most later mistakes.
Pre-startup conditions |  | The last physical checks before material goes in: housekeeping, blinds, inerting or purging, utilities and closed permits. These rows come from the earlier checklist; HSE lists inert gas purging among start-up hazards.
Evidence reference |  | A Yes with no pointer cannot be checked later. The reference (certificate number, loop sheet, minutes, permit number) lets someone else find what the answer rested on.
Open items |  | Every No and every action finished after start-up is written here with an owner, a due date and whether it blocks start-up. The US rule does not say what may stay open; the column is the form's own so the decision is made on a list rather than a feeling.
Start-up decision |  | One recorded decision, with its conditions, who made it and when, and when chemicals were first introduced, so the order of events can be shown. The US standard says what the review confirms, not who decides.
Independence of the authoriser |  | The form's own rule: the person who authorises start-up is not the PSSR lead, not the requester of the change and not the owner of the schedule or cost, because those people have a reason to want the start-up to go ahead. Neither the US text nor HSE's pages opened for this page require it.
Sign-off |  | Each signature says the signer checked the groups written against their name and agrees with the answers and the open items; the site manager's line is the final approval.

## Example (illustrative)
Illustrative example: invented, describes no real organisation
New inlet separator tied into a gas gathering station (invented plant)
Section | Entry
Review record | PSSR-2026-014. Gas gathering station, inlet area. Change reference MOC-2026-031 (project P-212). Scope: modified facility, a new inlet separator tied into the existing inlet header, so the process safety information changes. Raised by the project engineer. Review held 12 November; planned start-up 16 November. Chemicals to be introduced: natural gas and condensate through the new tie-in. Lead: the process engineer.
Reviewers | Process engineer (groups A, C, D, G), operations supervisor (C, E, H), maintenance supervisor (A, B, C), HSE adviser (B, D, F), instrument technician (A, B). The HSE adviser and the instrument technician did not design or build the separator.
Checks | 40 rows: 33 Yes + 4 No + 3 N/A = 40. N/A with reasons: A6 (no rotating equipment in this change), E3 (no contractors on the start-up), F4 (an MOC was raised). The 4 No answers: A8 (loop check of level transmitter LT-201 not signed), D2 (one PHA recommendation, a second high-level alarm, not yet in service), C3 (maintenance procedure for the new drain valves not issued), G1 (P&ID mark-up not yet approved).
Open items | 5 items: (1) A8 loop check, owner instrument technician, due 13 November, blocks start-up. (2) D2 second high-level alarm, owner process engineer, due 13 November, blocks start-up. (3) G1 P&ID approval, owner project engineer, due 14 November, blocks start-up. (4) C3 maintenance procedure, owner maintenance supervisor, due 30 November, does not block; risk accepted by the site manager. (5) Tag labels on six valves, from the A2 walk-down punch list, owner operations supervisor, due 23 November, does not block.
Start-up decision | Authorised with conditions at 14:00 on 15 November by the site manager. 3 blocking items raised, 3 closed (items 1 and 2 on 13 November, item 3 on 14 November), closure checked by the instrument supervisor, not the owners. Every row answered. Conditions: items 4 and 5 are closed by 30 and 23 November. Gas first introduced at 06:30 on 16 November, after the planned start.
Independence of the authoriser | All three boxes ticked: the site manager did not lead the review (the process engineer did), did not raise the change (the project engineer did) and does not own the project schedule or cost (the project manager does). No second authoriser needed.
Sign-off | Six lines signed on 15 November: PSSR lead, operations lead, process engineer, HSE representative, maintenance lead and the site manager as final approval.

## About
Template | Pre-Startup Safety Review (PSSR) Template
Printable form | /downloads/templates/pre-startup-safety-review-template.pdf
Page | https://qhsetech.com/templates/pre-startup-safety-review-template
Last updated | 2026-10-20
Note | General template, not legal or certification advice. Adapt it to your own procedures and to the requirements that apply to you.
What this workbook is | A spreadsheet for typing and for keeping a log. The PDF is the printable form. This file adds no formula and no rule.