## Fill in
Root Cause Analysis Worksheet Template
qhsetech.com/templates/root-cause-analysis-worksheet-template ¦ General template, not legal or certification advice. Adapt it to your own procedures and to the requirements that apply to you. ¦ Free template by QHSEtech, CC BY 4.0: reuse and adapt it with credit (see the About sheet)
No. | Action: what will change | For causal factor or root cause | Corrective or preventive | Kind (E, S, H or M) | Owner (role) | Due | Done on | Effectiveness check: what, when, by whom | Result

## Example (illustrative)
Illustrative example: invented, describes no real organisation
The action tracker from an invented investigation of a hand cut at a goods-in dock on 14 March, picking up the hand-off in the incident report template's worked example (invented site, people, records and dates)
No. | Action: what will change | For causal factor or root cause | Corrective or preventive | Kind (E, S, H or M) | Owner (role) | Due | Done on | Effectiveness check: what, when, by whom | Result
A1 | Remove fixed blades from the tool boards on all three docks and issue safety cutters | CF1: fixed-blade knife used to cut straps (E1, E5) | Corrective | S | Shift lead | 15 March | 15 March | Three unannounced tool-board checks on each dock in March and April; EHS lead | No fixed blade found: closed 30 April
A2 | Put safety cutters and spare blades on the stores reorder list with a minimum stock, and require EHS approval before a cutting tool is bought locally | RC1: cutting tools not controlled as safety items (E3, E7) | Corrective | M | Stores manager | 21 March | 20 March | Stock records and the purchase card log for April to June: any stock-out, any local purchase; EHS lead, 30 June | Neither found: closed 30 June
A3 | Ask the supplier to replace straps with tear-off tabs; until then, issue a guarded hook cutter for straps | CF3: straps added by the supplier in February (E6) | Corrective | E (interim cutter: S) | Purchasing manager | 31 May | Cutter 18 March; tabs from 12 May | Goods-in check of that supplier's pallets for four weeks after the change; dock supervisor | Open: check runs to 9 June
A4 | Add changes to incoming packaging to the site's change review, so goods-in tasks are reassessed before a new format arrives | RC2: packaging change not reviewed for its effect at the dock (E4, E6) | Preventive | M | Operations manager | 31 May | 28 May | The next two packaging changes at any goods-in area went through the change review with the task assessment updated; internal audit, September | Open until the September audit
A5 | Add unwrapping and strap cutting to the dock procedure and its task risk assessment, and brief all three shifts | CF1 and RC2: task missing from the procedure (E4) | Corrective | H | Dock supervisor | 28 March | 27 March | Watch two pallets opened on each shift in April and ask the operators what the procedure says; safety representative | April check failed on nights (not briefed); re-briefed 22 April; May check passed: closed 31 May

## About
Template | Root Cause Analysis Worksheet Template
Printable form | /downloads/templates/root-cause-analysis-worksheet-template.pdf
Page | https://qhsetech.com/templates/root-cause-analysis-worksheet-template
Last updated | 2026-10-22
Note | General template, not legal or certification advice. Adapt it to your own procedures and to the requirements that apply to you.
What this workbook is | A spreadsheet for typing and for keeping a log. The PDF is the printable form. This file adds no formula and no rule.
Licence and source | Creative Commons Attribution 4.0 International (CC BY 4.0), https://creativecommons.org/licenses/by/4.0/. You may copy, adapt and share this file, also commercially, if you give credit, link to the licence and say if you changed it. Credit line: Root Cause Analysis Worksheet Template by QHSEtech (https://qhsetech.com/templates/root-cause-analysis-worksheet-template), licensed under CC BY 4.0 (https://creativecommons.org/licenses/by/4.0/). Template page: https://qhsetech.com/templates/root-cause-analysis-worksheet-template